## Sheet1
TRM Domain | SBP Requirement | Current Status | Gap Identified | Action Plan | Target Date | Owner
Technology Governance | TRMF established with board-approved policies | Not in place | No TRMF or documented policies | Form governance team; draft & approve policies | Aug 2025 | IT Risk Lead
Board Oversight | Board IT Committee active | Partial | No formal reporting structure | Formalize board reporting | Jul 2025 | CISO
CISO Appointment | Independent CISO with sufficient authority | In progress | Role combined with CTO | Appoint dedicated CISO | Jun 2025 | HR
Asset Management | Maintain inventory of all critical assets and dependencies | Partial | Inventory incomplete | Update inventory & classify assets | Jul 2025 | IT Ops
Identity & Access Mgmt | MFA, least privilege, session timeout | Not compliant | MFA missing, session not managed | Implement IAM tools & policies | Sep 2025 | Security Team
Network Security | SOC, SIEM, segmentation, anti-malware | Partial | No SIEM, limited logging | Procure and deploy SIEM solution | Oct 2025 | Network Security Lead
Security Testing | Annual VA/PT & code reviews | Not started | No testing or schedule | Engage third-party for audits | Jul 2025 | DevSecOps
Data Security | Encryption, PCI-DSS, ISMS | In progress | PCI-DSS compliance incomplete | Enforce encryption, begin PCI-DSS | Sep 2025 | Compliance
Patch Management | Timely application of critical patches | Manual | Delayed patch cycles | Automate patching & test flows | Aug 2025 | IT Support
Incident Response | Board-approved IRP, reporting to SBP | Missing | No formal IRP or reporting SOP | Draft IRP, train staff | Jul 2025 | Security Team
Fraud Risk Management | End-to-end digital fraud monitoring | Basic | No cool-off, limited alerts | Implement fraud analytics tools | Oct 2025 | Risk & Fraud Officer
Outsourcing Risk | Due diligence, SBP approval, contract clauses | Partial | No vendor exit clauses | Revise vendor contracts | Sep 2025 | Legal
BCP/DR | DR in separate seismic zone, 6-monthly drills | In progress | No BCP testing done | Plan BCP drills with third parties | Oct 2025 | BCP Manager
Tech Audit | Annual independent audits | Not in place | No tech audit done yet | Schedule audit post pilot | Nov 2025 | Internal Audit